## ※Project Master
Project Identity |  |  |  | Timeline |  |  |  |  | Financial Metrics | [10 empty] | Location & Region |  |  |  | Team & Roles
Proposal NO. | Project NO. | Project Name CN | Project Name EN | Yearly | Status | Current Stage | Start Date | Dead line | Inv Amount total（RMB） | Partial Pay in Inv Cur total | O/S Amt total | Target Currency | Inv Amount total in Target Currency | Partial Pay in Inv Cur total in Target Currency | O/S Amt total in Target Currency | Next Payment Due | Payment Status | Next Payment Status | Collection Progress | City | Province | Province / 省份 | Area (Region) | Director | Leader | Project Total Effort | Related Payment | Related Task
1111 | P210231 | 项目1 | project 1 | 2026 | Cancelled | SPA I | 2026/4/1 | 2026/4/15 | ¥111,111.00 | ¥0.00 | ¥222,222.00 | US Dollar ($) | 15,325.66 | 0.00 | 30,651.31 | 2026/4/27 | ❗Overdue | SPA II | 0% |  | 北京市 | 北京市 | Southeast Asia | Nam Son | Dexter Wang | 7.95 | SZ26-0022 | 3333,2222,1111,2222
2222 | P210232 | 项目2 | project 2 | 2025 | Prospect | SPA II | 2026/4/20 | 2026/4/30 | ¥22,222.00 | ¥1,231.00 | ¥333,333.00 | Euro (€) | 2,841.69 | 157.42 | 42,625.70 | 2026/5/30 | Not Overdue | 2TA | 0.37% |  | 河北省 | 河北省 | Greater China |  |  | 12.45
3333 | 2019063 | 项目3 | project 3 | 2023 | Active | 2TA | 2026/4/22 | 2026/5/20 | ¥3,333.00 | ¥12,222.00 | ¥444,444.00 | British Pound (£) | 363.07 | 1,331.37 | 48,414.38 | 2026/5/10 | Not Overdue | SPA I | 2.68% |  | 内蒙古自治区 | 内蒙古自治区 | Greater China |  |  | 13.65 |  | 4444
4444 | P210234 | 项目4 | project 4 | 2026 | On Hold | SPA I | 2026/4/27 | 2026/5/8 | ¥444,444.00 | ¥33,333.00 | ¥555,555.00 | Japanese Yen (¥) | 9,259,250.00 | 694,437.50 | 11,574,062.50 | 2026/6/15 | Not Overdue | SPA II | 5.66% |  | 北京市 | 北京市 | Greater China |  |  | 9.30 | SZ26-0022 | 3333,2222,1111,2222
5555 | P210235 | 项目5 | project 5 | 2022 | At Risk | SPA II | 2026/5/1 | 2026/5/31 | ¥10,000,000.00 | ¥4,444.00 | ¥11,666,666.00 | Taiwan Dollar (NT$) | 44,642,857.14 | 19,839.29 | 52,083,330.36 | 2026/5/20 | Not Overdue | 2TA | 0.04% |  | 河北省 | 河北省 | Greater China |  |  | 9.45
6666 | 2019066 | 项目6 | project 6 | 2024 | Active | 2TA | 2026/4/20 | 2026/5/23 | ¥666,666.00 | ¥555,555.00 | ¥777,777.00 | Hong Kong Dollar (HK$) | 716,845.16 | 597,370.97 | 836,319.35 | 2026/5/25 | Not Overdue |  | 41.67% |  | 内蒙古自治区 | 内蒙古自治区 | Greater China |  |  | 9.90 |  | 4444

## Task Scheduling
Position | Proposal NO. | Project Name CN | Project Name EN | Team Leader | Assigned Manpower | Assigned Manpower-转文本 | Manpower Source | Support From | Task Description | Duration (h) | Manpower Utilization(Total) | Project Total Effort | Start Date | End Date | Status | Project Code | Notes
Designer | 1111 | 项目1 | project 1 | Andrew/Nam Son | Nam Son | Nam Son | BCI Shanghai | VHS HCM | SU Model and Rendering | 1.5 | 4.50 | 7.95 | 2026/4/20 | 2026/5/15 | Cancelled | 项目4,项目1
Graphics | 2222 | 项目2 | project 2 | Andrew/Nam Son | Jessica Chen | Jessica Chen | VHS HCM (Vietnam) | BCI Shanghai | SU Model and Rendering | 4.5 | 12.15 | 12.45 | 2026/4/21 | 2026/5/10 | Prospect | 项目4,项目1
Graphics | 3333 | 项目3 | project 3 | Andrew/Nam Son | Micaella | Micaella | VHS HCM (Vietnam) | BCI Shanghai | SU Model and Rendering | 4.5 | 4.50 | 13.65 | 2026/4/21 | 2026/5/10 | Prospect | 项目4,项目1
Softscape / Planting | 4444 | 项目4 | project 4 | Nam Son | Dexter Wang | Dexter Wang | VHS HCM (Vietnam) | BKT Bangkok | SU Model and PS Entrance G/F | 4.5 | 6.75 | 9.3 | 2026/4/20 | 2026/4/30 | On Hold | 项目6,项目3
Designer | 5555 | 项目5 | project 5 | Nam Son | Muj Huang | Muj Huang | VHS Hanoi | BCI Beijing | SU Modeling Task | 1.8 | 4.95 | 9.45 | 2026/4/22 | 2026/5/20 | Active
Graphics | 6666 | 项目6 | project 6 | Nam Son/Dexter | Jessica Chen | Jessica Chen | VHS HCM (Vietnam) | BCI Shanghai | SU Update as Design / color Plan | 3.15 | 12.15 | 9.9 | 2026/4/27 | 2026/5/8 | At Risk
Softscape / Planting | 1111 | 项目1 | project 1 | Jessica | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou | Perspective Adjustments | 1.8 | 14.55 | 7.95 | 2026/5/1 | 2026/5/31 | Completed
Designer | 2222 | 项目2 | project 2 | Dexter | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou | Develop & Revise 3D for Plot B/C & Park 1 | 3.15 | 14.55 | 12.45 | 2026/4/20 | 2026/5/23
Graphics | 3333 | 项目3 | project 3 | Dexter | Jenzel | Jenzel | VHS HCM (Vietnam) | VHS HCM | SU Model and Rendering | 1.5 | 4.50 | 13.65 | 2026/5/4 | 2026/5/18
Softscape / Planting | 4444 | 项目4 | project 4 | Dexter | Nam Son | Nam Son | BCI Shanghai | VHS HCM | SU Model and Rendering | 3 | 4.50 | 9.3 | 2026/4/20 | 2026/5/22
Designer | 5555 | 项目5 | project 5 | Muj | Jessica Chen | Jessica Chen | VHS HCM (Vietnam) | BCI Shanghai | Complete Remaining Softscape Plans & Revise | 4.5 | 12.15 | 9.45 | 2026/4/23 | 2026/5/15
Graphics | 6666 | 项目6 | project 6 | Jessica | Dexter Wang | Dexter Wang | VHS HCM (Vietnam) | BKT Bangkok | Garden Design (Continuation) | 2.25 | 6.75 | 9.9 | 2026/5/1 | 2026/5/28
Softscape / Planting | 1111 | 项目1 | project 1 | Jessica | Muj Huang | Muj Huang | VHS Hanoi | BCI Beijing | MLP Design / Colored Plan | 3.15 | 4.95 | 7.95 | 2026/4/25 | 2026/5/12
Designer | 2222 | 项目2 | project 2 | Jessica | Tung Nguyen | Tung Nguyen | BCI Guangzhou | BCI Shenzhen | CD / MLP Perspectives Monitoring/Review | 1.8 | 6.30 | 12.45 | 2026/4/27 | 2026/5/20
Designer | 3333 | 项目3 | project 3 | Jessica | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou | Design Perspective Monitoring | 3.15 | 14.55 | 13.65 | 2026/4/21 | 2026/5/8
Graphics | 1111 | 项目1 | project 1 |  | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou |  | 1.5 | 14.55 | 7.95 | 2026/5/2 | 2026/5/30
Softscape / Planting | 2222 | 项目2 | project 2 | Andrew | Jenzel | Jenzel | VHS HCM (Vietnam) | VHS HCM | Design | 3 | 4.50 | 12.45 | 2026/4/24 | 2026/5/16 |  | 项目4,项目1
Designer | 3333 | 项目3 | project 3 | Tuan | Tung Nguyen | Tung Nguyen | BCI Guangzhou | BCI Shenzhen | Update PS / Color Plan | 4.5 | 6.30 | 13.65 | 2026/4/22 | 2026/5/25
Graphics | 4444 | 项目4 | project 4 | Philip | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou | CD Design | 1.8 | 14.55 | 9.3 | 2026/4/26 | 2026/5/18
Softscape / Planting | 5555 | 项目5 | project 5 | Jessica | Tuan Pham | Tuan Pham | VHS HCM (Vietnam) | BCI Guangzhou | Perspective Monitoring / Review | 3.15 | 14.55 | 9.45
Designer | 6666 | 项目6 | project 6 | Andrew |  |  |  | External | Concept design and schematic layout for Test project phase 1 | 4.5 | 4.50 | 9.9 | 2026/4/25 | 2026/5/15 | Active |  | Initial task allocation, pending client feedback on design direction

## China Provinces
Province Name (CN) | Province Name (EN) | Region | Sort Order | 关联
北京市 | Beijing | 华北 |  | 项目4,项目1
天津市 | Tianjin | 华北
河北省 | Hebei | 华北 |  | 项目5,项目2
山西省 | Shanxi | 华北
内蒙古自治区 | Inner Mongolia | 华北 |  | 项目6,项目3
辽宁省 | Liaoning | 东北
吉林省 | Jilin | 东北
黑龙江省 | Heilongjiang | 东北
上海市 | Shanghai | 华东
江苏省 | Jiangsu | 华东
浙江省 | Zhejiang | 华东
安徽省 | Anhui | 华东
福建省 | Fujian | 华东
江西省 | Jiangxi | 华东
山东省 | Shandong | 华东
河南省 | Henan | 华中
湖北省 | Hubei | 华中
湖南省 | Hunan | 华中
广东省 | Guangdong | 华南
广西壮族自治区 | Guangxi | 华南
海南省 | Hainan | 华南
重庆市 | Chongqing | 西南
四川省 | Sichuan | 西南
贵州省 | Guizhou | 西南
云南省 | Yunnan | 西南
西藏自治区 | Tibet | 西南
陕西省 | Shaanxi | 西北
甘肃省 | Gansu | 西北
青海省 | Qinghai | 西北
宁夏回族自治区 | Ningxia | 西北
新疆维吾尔自治区 | Xinjiang | 西北
香港特别行政区 | Hong Kong | 港澳台
澳门特别行政区 | Macau | 港澳台
台湾省 | Taiwan | 港澳台

## Team Roster
User Name | Title (Role) | Is Team Leader | Team | Area (Region) | Email | Manpower Utilization(Total) | Manpower Source | Support From | Related Project | Related Task | Director Project | Leader Project
Nam Son | Associate Director | Y | Design | Southeast Asia |  | 4.5 | BCI Shanghai | VHS HCM |  | 4444,1111 | 项目1
Jessica Chen | Senior LA | Y | Design | Greater China |  | 12.15 | VHS HCM (Vietnam) | BCI Shanghai |  | 6666,5555,2222
Dexter Wang | Senior LA | Y | Design | Greater China |  | 6.75 | VHS HCM (Vietnam) | BKT Bangkok |  | 6666,4444 |  | 项目1
Andrew Liu | Graphics Lead | Y | Graphics | Greater China |  |  | VHS HCM (Vietnam) | BCI Shanghai
Muj Huang | Softscape Lead | Y | Softscape / Planting | Greater China |  | 4.95 | VHS Hanoi | BCI Beijing |  | 1111,5555
Tung Nguyen | Senior Designer | Y | Design | Southeast Asia |  | 6.3 | BCI Guangzhou | BCI Shenzhen |  | 3333,2222
Tuan Pham | Graphics Artist | N | Graphics | Southeast Asia |  | 14.55 | VHS HCM (Vietnam) | BCI Guangzhou |  | 4444,5555,1111,3333,2222,1111
Shasha Li | CAD Team Leader | Y | CAD / HDD | Greater China |  |  | VHS HCM (Vietnam) | External
Jenzel | Graphics Artist | N | Graphics | Southeast Asia |  | 4.5 | VHS HCM (Vietnam) | VHS HCM |  | 2222,3333
Micaella | SU Modeler / Graphics | N | Graphics | Southeast Asia |  | 4.5 | VHS HCM (Vietnam) | BCI Shanghai |  | 3333
Miko | SU Modeler / Graphics | N | Graphics | Southeast Asia |  |  | BCI Shanghai | BKT Bangkok
Art | Senior Designer | N | Design | Greater China |  |  | BCI Shanghai | BCI Shanghai
Yoko Tanaka | CAD Specialist | N | CAD / HDD | Greater China |  |  | BCI Shanghai | BCI Beijing
Sheila | Planting Designer | N | Softscape / Planting | Greater China |  |  | BCI Shanghai | BCI Shenzhen
Philip | Designer | N | Design | Greater China |  |  | BCI Shanghai | BCI Guangzhou
Vasinee | Designer | N | Design | Southeast Asia |  |  | BCI Shanghai | External
Andres | CAD Specialist | N | CAD / HDD | Southeast Asia |  |  | BCI Shanghai | VHS HCM
Gee | CAD / HDD Specialist | N | CAD / HDD | Southeast Asia |  |  | BCI Shanghai | BCI Shanghai
Eduardo | CAD Specialist | N | CAD / HDD | Southeast Asia |  |  | BCI Shanghai | BKT Bangkok
Michael | HDD Specialist | N | CAD / HDD | Southeast Asia |  |  | BCI Shanghai | BCI Shanghai
Jocelyn | Designer (DD) | N | Design | Southeast Asia |  |  | BCI Shanghai | BCI Beijing
Fernando | Designer | N | Design | Greater China |  |  | VHS HCM (Vietnam) | BCI Shenzhen
Earth | Graphics Artist | N | Graphics | Greater China |  |  | VHS HCM (Vietnam) | BCI Guangzhou
[6 empty] | 4.5 |  | External

## Stage Definition
Stage | Stage_describe | type | 关联 | 关联 1
FS | Feasibility Study | VN Stage
MPP | Master Planning Plan | VN Stage
AS | Authorship Supervision | VN Stage
SPA I | Site Plan Audit I (Overall Planning Evaluation I) <For Fixed Planning Scheme> | Landscape Design or Planning Stage | 项目4,项目1 | 项目3
SPA II | Site Plan Audit II (Overall Planning Evaluation II) <For Unfixed Planning Scheme> | Landscape Design or Planning Stage | 项目5,项目2 | 项目1,项目4
2TA | 2 Themes Approach (Exploration of Two Design Concepts) | Landscape Design or Planning Stage | 项目6,项目3 | 项目2,项目5
MLP | Master Landscape Plan (Overall Landscape Concept Layout) | Landscape Design Stage
PCD | Preliminary Conceptual Design (Concept Exploration) | Landscape Design Stage
FCD | Final Conceptual Design (Schematic Design) | Landscape Design Stage
FMLP | Final Master Landscape Plan (Final Overall Landscape Concept Layout) | Landscape Design or Planning Stage
HDD1 | Hardscape Design Development 1 (Hardscape Expansion - Preliminary Design) | Landscape Design Stage
SDD1 | Softscape Design Development 1 (Softscape Expansion - Preliminary Design) | Landscape Design Stage
DD1 | Design Development 1 | Special Stage
HDD2 | Hardscape Design Development 2 (Hardscape Expansion - Detailed Design) | Landscape Design Stage
SDD2 | Softscape Design Development 2 (Softscape Expansion - Detailed Design) | Landscape Design Stage
DD2 | Design Development 2 | Special Stage
PSO | Project Scheduling and Operations | Project Scheduling and Operations
HWD | Hardscape Working Drawing (Hardscape Construction Drawing) | Landscape Design Stage
SWD | Softscape Working Drawing (Softscape Construction Drawing) | Landscape Design Stage
TR | Tender Review (Construction Drawing Review) | Landscape Design Stage
SO | Site Observation (Landscape Construction Inspection) | Landscape Design Stage
Remarks | Remarks | Special Stage
BDS | BD Support | Special Stage

## Payment Tracker
Total
Project Manager | Project Code | Project # | Project Name | Invoice Date | Invoice # | Inv Cur | Inv Amount | Partial Pay in Inv Cur | O/S Amt | Forecast Payment Month | Follow up situation | 关联 | Inv Amount total | Partial Pay in Inv Cur total | O/S Amt total
Jessica | P210231 | 项目4,项目1 | Hangzheng Chuchu [2023] Lot 85 Phase 2 and Phase 3 祐政赫儲出[2023]85號地塊二期 三期 : PH2: 100% WD | 2026/4/10 | SZ26-0022 | US Dollar ($) | 111111 | 0 | 222222 | 2026/4/22 | 待招标完成后才能申请支付 |  | ¥111,111.00 | ¥0.00 | ¥222,222.00
| P210232 |  |  |  |  | Euro (€) | 22222 | 1231 | 333333 |  |  |  | ¥22,222.00 | ¥1,231.00 | ¥333,333.00
| 2019063 |  |  |  |  | British Pound (£) | 3333 | 12222 | 444444 |  |  |  | ¥3,333.00 | ¥12,222.00 | ¥444,444.00
| P210234 |  |  |  |  | Japanese Yen (¥) | 444444 | 33333 | 555555 |  |  |  | ¥444,444.00 | ¥33,333.00 | ¥555,555.00
| P210235 |  |  |  |  | South Korean Won (₩) | 10000000 | 4444 | 11666666 |  |  |  | ¥10,000,000.00 | ¥4,444.00 | ¥11,666,666.00
| 2019066 |  |  |  |  | Hong Kong Dollar (HK$) | 666666 | 555555 | 777777 |  |  |  | ¥666,666.00 | ¥555,555.00 | ¥777,777.00

## Exchange Rate Reference
Code | Chinese Name | English Name | Exchange Rate (to CNY)
| 美元 | US Dollar ($) | 7.25
| 欧元 | Euro (€) | 7.82
| 英镑 | British Pound (£) | 9.18
| 日元 | Japanese Yen (¥) | 0.048
| 韩元 | South Korean Won (₩) | 0.0053
| 港币 | Hong Kong Dollar (HK$) | 0.93
| 新台币 | Taiwan Dollar (NT$) | 0.224
| 俄罗斯卢布 | Russian Ruble (₽) | 0.079
| 印度卢比 | Indian Rupee (₹) | 0.086
| 澳元 | Australian Dollar (A$) | 4.68
| 加元 | Canadian Dollar (C$) | 5.36
| 新加坡元 | Singapore Dollar (S$) | 5.35
| 泰铢 | Thai Baht (฿) | 0.198
| 越南盾 | Vietnamese Dong (₫) | 0.00029
| 马来西亚林吉特 | Malaysian Ringgit (RM) | 1.55
| 菲律宾比索 | Philippine Peso (₱) | 0.126
| 印尼盾 | Indonesian Rupiah (Rp) | 0.00045
| 阿联酋迪拉姆 | UAE Dirham (د.إ) | 1.97
| 沙特里亚尔 | Saudi Riyal (﷼) | 1.93
| 巴西雷亚尔 | Brazilian Real (R$) | 1.26
| 南非兰特 | South African Rand (R) | 0.39
| 土耳其里拉 | Turkish Lira (₺) | 0.22
| 巴基斯坦卢比 | Pakistani Rupee (₨) | 0.026
| 埃及镑 | Egyptian Pound (E£) | 0.146
| 哈萨克斯坦坚戈 | Kazakhstani Tenge (₸) | 0.015
| 肯尼亚先令 | Kenyan Shilling (KSh) | 0.056
| 尼日利亚奈拉 | Nigerian Naira (₦) | 0.0044
| 瑞士法郎 | Swiss Franc (CHF) | 8.02

## 日报
文本 | Project NO.-去重引用 | 人员 | 数字 | 日期
P210231